## Sheet1
Sprint | Included User Stories | Task ID | Sprint Task | Suggested Responsible Role (edit to real member) | Estimate (hours) | Status | Definition of Done
Sprint 1 | Project Planning | T-1 | Take place team meeting and discuss about the project and requirements. | Scrum master and the whole team | 1 hour | Done | Team meet via zoom and talkd about the project and project requirments.
Sprint 1 | Team Orgnization | T-2 | Assign team roles and responsibilities | Scrum master and the whole team | 1 hour | Done | Determining the roles and responsibilities of group memebers
Sprint 1 | US-1, US-2, US-3, sprint-backlog created | T-3 | Weibsite Features and point for improvment | Scrum master and the whole team | 1 hour | Done | It was discussed and determined which feature our weibsite should have. Break down Sprints work into tasks, assign responsibilities, estimate effort, and track progress.
Sprint 1 | US-1, US-2, US-20, product-backlog created | T-4 | Working on the homepage | Devloper | 6 hour | Done | The homepage part completed and run and the output included and nice welcome massages and some other details. Organize and prioritize the 20 user stories according to the project requirements.
Sprint 2 | US-02, US-03, US-04, sprint and product backlog | T-5 | Complete the About section and display room types with room photos. Discussed about sprint and product backlog. | Developer / UI designer | 6 hours | Done | The about section completed and it work correct and we have seen the output this part was information about hotel, Organize and prioritize the 20 user stories according to the project
Sprint 2 | US-05, The hotel website requirements | T-6 | Add room prices and clear price labels for each room type. functional and non-functional requirements of the hotel website. | Developer, Product Owner | 4 hours | Done | Both functional and non functional requirements completed and tallked about rooms detila
Sprint 2 | US-20, User Stories | T-7 | Create and connect the main navigation links between pages and sections. Listed all 20 user stories | Developer, whole team | 4 hours | Done | The created part of our system connected tougher and worked correctly. User stories completed
Sprint 2 | US-01–US-05, US-20, use case diagram | T-8 | Review the homepage, About section, room listings, and navigation. Use case diagram discussed. | Whole team | 3 hours | Done | The created part like homepage, about us and rooms reviewed and checked the codes and output
Sprint 3 | US-06, | T-9 | Show room availability so visitors can identify rooms available for their selected stay. | Developer, Scrum master | hours | Done | Created and completed the room availability which customer can see
Sprint 3 | US-07 | T-10 | Add a Book Now action that opens the booking form for the selected room. Sprint backlog 1, and 2 assigned | Developer, Scrum master | hours | Done | Break down Sprints work into tasks, assign responsibilities, estimate effort, and track progress.Booking part created and developed
Sprint 3 | US-08, US-09 | T-11 | Add guest name, email, and phone number fields to the booking form. | Developer / UI designer | hours | Done | The booking form page created and completed, it was information about customer to book room.
Sprint 3 | US-10,Use case diagram, burndown chart | T-12 | Add a room-type selector to the booking form. Use case diagram created to and created burndown chart of sprint 1, 2 | Developer | hours | Done | Create a use case diagram showing the main actors and their interactions with the hotel website.
Sprint 4 | US-11, US-12 | T-13 | Add check-in and check-out date fields to the booking form. | Developer | hours | In progress
Sprint 4 | US-13, Sequence diagram | T-14 | Validate required fields, contact details, and date order before accepting a booking request. Sequence diagram created | Developer / Tester | hours | In progress | Create a sequence diagram showing interactions related to the selected website functionality.
Sprint 4 | US-14 | T-15 | Display a booking confirmation after a valid booking request is submitted. | Developer | hours | In progress
Sprint 4 | US-07–US-14 | T-16 | Test the complete booking journey from selecting a room to receiving confirmation. | Whole team | hours | In progress
Sprint 5 | US-15 | T-17 | Create database storage for guest/customer details. | Backend developer | hours | In progress
Sprint 5 | US-16 | T-18 | Create and connect room and booking records in the database. | Backend developer | hours | In progress
Sprint 5 | US-13–US-16 | T-19 | Connect booking validation and confirmation to the data-storage process. | Developer | hours | Planned
Sprint 5 | US-15, US-16 | T-20 | Test saving, retrieving, and checking customer, room, and booking records. | Backend developer / Tester | hours | Planned
Sprint 6 | US-17 | T-21 | Create a staff report showing booking totals and room status. | Developer | hours | Planned
Sprint 6 | US-18 | T-22 | Build a contact form for visitors to send questions to the hotel. | Developer / UI designer | hours | Planned
Sprint 6 | US-19 | T-23 | Make the website responsive for mobile phones, tablets, and desktop screens. | Frontend developer / Tester | hours | Planned
Sprint 6 | US-01–US-20 | T-24 | Run final system testing, fix high-priority defects, and review the website against the product backlog. | Whole team | hours | Planned